## 工作表1
| 項目 | 次項目 | 細項 | QCN | Hard Coding | PIC | 建議導入時間 | Filter | Kirin | Corona | JEDI 實際導入情形 | Draco 實際導入情形 | 備註
QCN | 1st QCN | Definition check | 1. 比對Qualcomm Default Definition file 和 Asus Definition file差異 * Qualcomm Default Definition file Path: ..\Source\modem_proc\rfnv\etc\NvDefinition.xml * Asus Definition file : ASUS_NvDefinition_v23_20180105.xml * 方式 1) 以最新前一個案子或是上一版QCN Source + Qualcomm Default Definition file = 產生QCN_Qualcomm 2) 以最新前一個案子或是上一版QCN Source + Asus Definition file = 產生QCN_Asus 3) 比較兩個QCN差異，判斷是否要將QCN_Qualcomm 多出來的definition item加入 Asus Definition file 4) 已知Asus Definition多的definition item: | V |  |  | EVB |  | [7/17] EVB QCN VEE Done. KIRIN_hwid426_bid255_pid255_Master.xml + ASUS_NvDefinition_v23_20180105.xml == KIRIN_hwid426_bid255_pid255_Master.xml + NvDefinition.xml | [6/08] EVB QualcommDefinition+QualcommMasterfile.xqcn == AsusDefinition+QualcommMasterfile.xqcn
QCN |  | RF card | 1) 需要知道是用哪一張RF card 當作基底 NV#28967 | V |  |  | EVB |  | [7/04] EVB RF card ID: 413 hwid413_bid255_pid255 [7/13] EVB QCN VEE Done. RF card ID: 426 hwid426_bid255_pid255 | [6/08] EVB 377 SDM660_SDR660_APT_CHINA_4101_B71_MASTERFILE.xml
QCN |  | Master file | 若為Update 工廠Code base檢查 1.可以直接比較 Masterfile.xml, 2.若差異太大可用NV Tool產生QCN比較，再詢問RF Driver是否要加入修改。 | V |  |  | Every stage |  |  | [6/08] EVB no use
QCN |  | Marketing Spec | 需要對照Marketing SPEC，新增Band Static RF NV | V |  |  | EVB |  | [7/13] EVB QCN VEE Done. EVB marketing spec RF Card 426 + 427 GSM:2/3/5/8 WCDMA:1/2/3/4/5/6/8/19 LTE:1/2/3/4/5/7/8/12/17/18/19/20/26/28/29/30/32/34/38/39/40/41 TDSCDMA: 34/39 CDMA: BC0 LAA: Yes WCDMA B5 = B6 + B19 LTE B29/ 32 /46 only Rx | [6/08] EVB Check marketing spec: GSM:2/3/5/8 WCDMA:1/2/3/4/5/6/8/19 LTE:1/2/3/4/5/7/8/12/17/18/19/20/26/28/32/34/38/39/40/41 TDSCDMA: none CDMA: none LAA: none [6/11] Add WCDMA B3 and LTE B18/19/20/32 at SDM660_SDR660_HCMMPA_ROW_MASTERFILE.xml ,by AS/Apache
QCN |  | PA states | 修改xxx_TX_STATIC_DATA_I 的 number_of_active_pa_states and pa_range_map a. number_of_active_pa_states = 2 / pa_range_map = 1 0 (disable XPT) b. number_of_active_pa_states = 3 / pa_range_map = 2 1 0 (EPT) | V |  |  | EVB |  | [7/17] EVB QCN VEE Done. RF Driver Apache: a. number_of_active_pa_states = 2 / pa_range_map = 1 0 (disable XPT) | [6/11] Modified xxx_TX_STATIC_DATA_I Disable XPT - number_of_active_pa_states = 2 / pa_range_map = 1 0,by AS/Apache
QCN |  | XPT | 4) 修改xpt_config a. xpt_config = 0 (disable XPT) b. xpt_config = 2 (EPT) | V |  |  | EVB |  | [7/13] make sure volterra_mode = Disable / autopin_mode = Disable / autodelay_mode = Disable / dpd_mode = use DPD stored for with memory calibratioin, base on kernal config stored in multilin cal NV [7/17] EVB QCN VEE Done. RF Driver Apache: a. xpt_config = 0 (disable XPT) | [6/11] Disable XPT xpt_config = 0 by RF/Driver Apache 20180611
QCN |  | Remove CA Combo | Remove NV#28874 RFNV_LTE_CA_BW_CLASS_COMBO_I, |  |  |  | ER |  | [7/17] EVB QCN VEE Done. RF Driver Apache: Remove NV #28874
QCN |  | SIM hotswap | NV#70210判斷Hot swap active high or low | V |  |  | ER |  |  | [6/11] 電路圖不完整，等EVB完整電路圖機台。
QCN |  | TAR |  |  | V |  | ER |  | [8/10] SDM8150 TAR function is differnet with SDM845.
QCN |  | Review AS NV/EFS |  |  |  |  | ER
QCN |  | Review NAS NV/EFS |  |  |  |  | ER
QCN |  | Review GPS NV/EFS |  |  |  |  | ER |  | [7/04] GPS/JeremyChiang provide ZF6 GPS NV. [7/10] EVB QCN VEE Done. Implement ZF6 GPS NV. | [7/04] GPS/JeremyChiang provide ZF6 GPS NV. [7/10] Implement ZF6 GPS NV.
MBN | 1st MBN | Remove cust HW/SW MBN | SAR | [5 empty] | [7/12] Corona and Kirin implement NO customer MBN. | [7/12] Corona and Kirin implement NO customer MBN.
RF | SAR | SAR initial Value | 1. LTE : sar_tx_power_limit_dB10 = 230 2. WCDMA: sar_mtpl_dbm10 = 240 3. GSM: NV#29194~29197 4. CDMA: RFNV_DATA_TYPE_CDMA_VARIANT_SAR 5. TDSCDMA: no need | V |  | RF Driver Driver | ER |  | [7/17] EVB QCN VEE Done. | [6/11] EVB QCN: SAR initial Value 1. LTE : sar_tx_power_limit_dB10 = 230 2. WCDMA: sar_mtpl_dbm10 = 240 3. GSM: NV#29194~29197, by AS/Apache 20180611 | [4/19] ER QCN V1, default SAR value. [4/25] ER2 QCN V2, tune WCDMA from 230 to 240. | [12/19] ER QCN V1 WCDMA default SAR, RF driver provide [2/27] PR QCN v6, Add LTE/GSM/TDSCDMA, RF driver provide. [3/02] PR QCN v7, Remove TDSCDMA SAR value.RF driver comment. | [5/09] 詢問冠宇，Default SAR Value需要給Tx Max Power,若BSP啟動SAR，才不會被降Power。 [5/11] 詢問David/KuanYu ，如果SAR機制被啟動, 會根據手機”當下的Max Power”和”SAR Power”取較小值當最後的Max Tx Power，所以初期設定default SAR為Tx Max power, 不會發生因apply SAR反而讓DUT打出更大的Power [5/14] Joseph:既然 SAR 被啟動 & “防呆: 解決 RF 的值不存在 (or 沒給)”，所以如果default是 “UE Max. Tx Power” 就沒有SAR(降 Tx Power) 的效果。因此，直觀上default 應該至少要UE Max. Tx Power減 1~2 dB。 [5/22] 詢問冠宇，建議RD研發階段SAR Value設為Tx Max Power. 不建議直接幫RF決定SAR值，否則performance 不會符合預期。 實際打出來的 Power = min ( RF tune Tx Max Power , SAR value)
RF | SAR | SAR Table | 1.RF Provide SAR Value and scenario. 2.BSP/RIL implement SAR scenario. | V |  | RF BSP/RIL | PR後期~MP | V |  |  | [7/30] RF Driver/Jeff will implement SAR at QCT_SDM845_M3.15.35-MP / QCT_SDM845_Dev. | [4/23] RF Lose, RF Driver Hard Coding Shipping.
RF | SAR | (Draco Only) | Always Enable SAR State=1 during RF common init | [8 empty] | [4/25] RF Request, RF Driver Hard coding. | Draco才要，RF Request.
RF | Tune Code | Algorithm | NV#26693 QCN = 2 ; Hard code = 6 (支援MAAT+ACL+OL) | V | V | RF RF Driver | QCN: ER Hard Coding: PR~MP |  | [7/16] EVB QCN VEE Done. Apache: NV#26693 QCN = 2 ; | [6/11] EVB QCN: NV#26693 QCN = 2 | [4/25] ER2 QCN V2, NV#26693 =2 | [1/08] ER QCN v2, NV#26693 = 2. ANT Request [2/27] PR QCN v6, NV#26693 = 6 (wrong) RF Request [3/23] PR2 QCN v10, NV#26693 = 2.RF correct [4/2] RF Driver Hard Coding depend on gcf mode flag.
RF |  | ACL | RF Provide NV#29452/ 29570 | V |  | ANT | PR~MP | V |  |  | [8/08] RF/Marco Lo provide ACL/MAAT. [8/14] Redownload QCN V8, | [2/27] PR QCN v6, RF request. [3/21] PR2 QCN v9, RF request. | RF再MP QCN前決定是否要開ACL/MAAT，並提供最終值。 [6/13] 修改PIC為ANT。
RF |  | MAAT | RF Provide NV#29451/ 29452/ 29570 | V |  | ANT | PR~MP | V |  |  | [8/08] RF/Marco Lo provide ACL/MAAT. [8/14] Redownload QCN V8, | [4/13] RF request enable MAAT, RF Driver Hard Coding. [4/13] RF request, Driver RedownLoad QCN because NV#29570 Size Structure can't hard coding.
RF |  | OL (open loop) | ANT provide NV#29578 RFNV_ATUNER_TREE_DATA_I | V |  | ANT | Every stage |  |  |  | [4/25] ER QCN V2, ANT provide. [5/17] ER2 QCN V3, ANT provide. [8/14] Redownload QCN V8, ANT/Jason provide. | [1/08] ER QCN V2, ANT provide. [1/17] ER2 QCN V3, ANT provide. [1/30] ER3 QCN V4, ANT provide. [2/27] PR QCN V6,ANT provide. | open loop 就是不對動態調整 close loop 就是會依據某些情況做動態調整 ex 因為手握造成performance 不好,會依據收訊的狀況調整tune code
RF | ASDiv | Initial | 1.Disable ASDiv NV#70245/ 70248/ 70240 | V |  | RF Driver Driver | ER |  |  | [6/11] EVB QCN: Disable ASDiv | [4/19] ER QCN V1 ,RF driver provide. | [12/19] ER QCN V1 ,RF driver provide. | [8/02] RF/Marco AsDiv是上下天線切換的參數。 AsDiv參數，就是我們會提供包含天線和硬體的Tx上下切換以及Rx0/Rx1 上下切換的差異表給你們評估是否需要調整Qualcomm default threshold 然後你們會請field trial team測試看有沒有問題
RF |  | LTE connect | 1.need hard code, depend on gcf mode flag (SIM1/SIM2) NV#70277/ 70248/ 73581/ 70240/ 70276 NV#70221/ 70245/ 70220/ 70298/ 70297 |  | V | ANT RF Driver | PR~MP | V |  |  | [7/02] RF Driver / Jeff hard coding at QCT_SDM845_M3.15.35-MP / QCT_SDM845_Dev | [4/2] RF driver,Hard coding, | 主要是用Qualcomm Default值，加上ANT Team提供Value,RF Driver再去修改。 需要測試才知道正確還是錯誤。
RF |  | LTE idle | 1.NV#70248 [11] = from 0 to 1 |  | V | RF Driver | PR~MP |  |  |  |  | [5/4] RF Driver lose, Hard coding. | Qualcomm Default為1
RF | WLAN Coex Operation Mode | cxm_mode | 1.若有LTE B46，詢問RF/RF Driver。 2.NV#73775 JEDI/Draco= 21 ; ARA/Titan =20( no ANT Sharing) | V |  | RF RF Driver Driver | ER |  |  | [6/11] Corona no LTEB46 | [5/17] ER2 QCN V3, RF request. | [1/17] ER2 QCN V3, RF request.
RF |  | Golden LAA QCN | 1. RF provide NV#29453 2. 須包含RSB資料 | V |  | RF | PR | V |  | [6/11] Corona no LTEB46 | [6/13] RF/Albert: 目前還屬於ER階段，等下個run 後期PR驗證/fine tune過後再提供，那個才會是final 的K data. [8/22] RF/Albert provided.MP QCN v.9 | [1/30] ER3 QCN V4, RF provide. [6/28] 未包含RSB資料，出版給CSC。 | 因CSC回流機台，沒有K/T B46的儀器，要求提供Golden LTE B46 放入Static QCN。Draco的做法為取50次K值平均。
RF |  | Bang Cofig | 1.需要針對不同國家進行修改Band |  | V | RF Driver | ER~ PR | V |  |  | [7/25] RF Driver / Jeff hard coding "ID" at QCT_SDM845_M3.15.35-MP / QCT_SDM845_Dev
RF | EFS | GSM CLPC close | 1. add EFS file /rf/clpc_disable.dat | V |  | RF | by case | V |  |  | [6/13] Draco 有在工廠TAR加入 RF/Albert需要支援GSM CLPC→ RF是想要導入GSM FBRx Calibration ? [Need RF provide : 想確認RF是想要導入GSM FBRx Calibration嗎?] [7/05] RF/Josh_JJ: GSM FBRx => RF確認不導入, need add efs at MP TAR. [7/12] PR2 QCN V6 implement disable clpc EFS file | [3/16] PR QCN V8, RF driver request. | Feed back RX